## Ark1
| Plan | [6 empty] | Design |  |  |  |  | Build | [6 empty] | Launch
| Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24
Project Manager | Project Management, Contracts, Customer Contact, Proposal | [6 empty] | Project Management, Customer Contact |  |  |  |  | Project Management, Customer Contact | [6 empty] | Project Management, Contracts, Customer Contact, Proposal
Project Manager Content Developer | Initial Meeting
Project Manager Content Developer Designer | Uncover Needs Identify Goals Project Planning
Content Developer Designer |  |  | Research
Project Planning Content Developer Designer |  |  |  | Strategy Meetings
Content Developer |  |  |  |  | Content Examination
Designer Font-End Developer Content Developer | [6 empty] | Layout/Structure | Layout and Structure
Designer | [8 empty] | Style Tiles
Project Manager Designer Customer | [11 empty] | Presentation StyleTile
Content Developer | [8 empty] | Text Content
Photograph | [8 empty] | Photoshoot Facilities |  | Photoshoot Products |  | Photoshoot Products
Designer Front-End Developer | [12 empty] | UI Planning |  |  |  |  | UI Testing
Front-End Developer | [12 empty] | Coding/Building site | [6 empty] | Coding/Building site
Front-End Developer Designer Content Developer | [19 empty] | Browser testing
Front-End Developer Designer | [21 empty] | Bugfixing
Project Manager Front-End Developer Designer Content Developer | [23 empty] | Launch